## Gantt Chart
	Projet S3 modes de scruttins				1%

	ALARY DORIAN TPA31 dorian.alary@univ-tlse3.fr		jeudi 25 novembre 2021
	EDINF3G1 : Projet S3 | 2021-2022
	Tuteur : Herzog
										46					47					48					49					50					51					52					01					02					03					04					05					06					07					08					09					10					11					12					13					14					15					16					17					18					19
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	nov.-21					déc.-21					janv.-22					févr.-22					mars-22					avr.-22					mai-22
			15-nov.-2021	41	10-janv.-2022	1%	57			15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14
	Code		15-nov.-2021	41	10-janv.-2022	1%	57	1	114
	Création environnement		15-nov.-2021	1	15-nov.-2021	100%	1	1	0
	Makefile		16-nov.-2021	2	17-nov.-2021	0%	2	0	2
	Fichier utils_sd		18-nov.-2021	5	22-nov.-2021	0%	5	0	5
	Module liste		23-nov.-2021	2	24-nov.-2021	0%	2	0	2
	Module lecture_csv		25-nov.-2021	6	30-nov.-2021	0%	6	0	6
	Main
	Analyse des options		15-nov.-2021	7	21-nov.-2021	0%	7	0	7
	Appel des différents programmes		22-nov.-2021	50	10-janv.-2022	0%	50	0	50
	Module uninominales		01-déc.-2021	3	04-déc.-2021	0%	4	0	3
	Module condorcet_minimax		05-déc.-2021	7	11-déc.-2021	0%	7	0	7
	Module condorcet_schulze		12-déc.-2021	7	18-déc.-2021	0%	7	0	7
	Module python afficher_graphe		19-déc.-2021	6	24-déc.-2021	0%	6	0	6
	Programme verify_my_vote		25-déc.-2021	7	29-déc.-2021	0%	5	0	7
	Tests, correction bugs, rattrapage du retard		30-déc.-2021	12	10-janv.-2022	0%	12	0	12

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays
		01/01/2014
		04/03/2014
		18/04/2014
		20/04/2014
		25/04/2014
		01/05/2014
		10/06/2014
		15/08/2014
		08/12/2014
		25/12/2014